## Database Schedule
Option | Server | Region | Database Set | Technical Owner | Functional Owner | Wk. of June 18 | Wk. of June 25 | Wk. of Jul 2 | Wk. of Jul 30 | Wk. of Aug 6 | Wk. of Oct 22 | Wk. of Oct 29 | Wk. of Nov 5 | Wk. of Nov 12 | Wk. of Nov 19 | Wk. of Nov 26 | Wk. of Dec 3 | Wk. of Dec 10 | Wk. of Dec 17 | Wk. of Dec 24 | Wk. of Dec 31
| Sand-cov7102 | xxxxxx | Training | J. Juarez | I. Dillaway | [5 empty] | EMEA Train | EMEA Train | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
| Sand-cov7102 | xxxxxx | Demo | J. Juarez | C. Gorman | [5 empty] | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo | Visteon Demo
| Sand-cov7102 | xxxxxx | Play | S. Hegel | J. Juarez | [5 empty] | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5 | .NET 2.5
11 | DEV-cov7103 | REG01 | GLD1 | J. Juarez | C. Theisen | .NET UI Build | .NET UI Build | Conversion | EDI/Dev | EDI/Dev | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy | EDI-IAP Copy
21 | DEV-cov7103 | REG01 | DEV1 | J. Juarez | G. Yang | .NET UI Build | .NET UI Build | Conversion | EDI/Dev | EDI/Dev | Development | Development | Development | Development | Development | Development | Development | Development | Development | Development | Development
31 | DEV-cov7103 | REG01 | CNV1 | J. Juarez | F. Shannon | Network Team | Network Team | Network Team | DS | DS | Data Migration | Data Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration | Pilot-Migration
22 | DEV-cov7103 | REG02 | DEV2 | J. Juarez | TBD | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
32 | DEV-cov7103 | REG02 | CNV2 | J. Juarez | F. Shannon | Unavailable | Unavailable | Unavailable | POC Load | POC Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load | CRP Load
23 | DEV-cov7103 | REG03 | CNV3 | J. Juarez | TBD |  |  |  | TBD | TBD | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
33 | DEV-cov7103 | REG03 | CNV3 | J. Juarez | TBD |  |  |  | TBD | TBD | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
24 | DEV-cov7103 | REG04 | DEV4 | J. Juarez | TBD | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
34 | DEV-cov7103 | REG04 | CNV4 | J. Juarez | TBD | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
25 | DEV-cov7103 | REG05 | DEV5 | J. Juarez | V. Lu |  |  |  | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV | Korea-DEV
35 | DEV-cov7103 | REG05 | CNV5 | J. Juarez | V. Lu |  |  |  | TBD | TBD | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
11 | QA-cov7202 | REG01 | TST1 | J. Juarez | M. Kirsch | Unavailable | .NET UI Build | .NET UI Build | DS-Training | DS-Training | DS Training | DS Training | DS Training | DS Training | DS Training | DS Training | DS Training | DS Training | DS Training | DS Training | DS Training
12 | QA-cov7202 | REG02 | TST2 | J. Juarez | S. Graf | Unavailable | .NET UI Build | .NET UI Build | POC 1-Trans | POC 1-Trans | Dry Run | Day in Life | Overview CRP | CRP | Thanksgiving | CRP | CRP | CRP | CRP | Post CRP | Post CRP
13 | QA-cov7202 | REG03 | TST3 | J. Juarez | S. Tryon |  |  |  | Unavailable | Unavailable | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test | CRP Test
14 | QA-cov7202 | REG04 | TST4 | J. Juarez | TBD | Unavailable | .NET UI Build | .NET UI Build | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
15 | QA-cov7202 | REG05 | TST5 | J. Juarez | V. Lu | Unavailable | .NET UI Build | .NET UI Build | TBD | TBD | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training | Korea-Training
21 | QA-cov7202 | REG01 | TRN1 | J. Juarez | S. Tryon | [5 empty] | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT
22 | QA-cov7202 | REG02 | TRN2 | J. Juarez | TBD | [5 empty] | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
23 | QA-cov7202 | REG03 | TRN3 | J. Juarez | TBD | [5 empty] | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
24 | QA-cov7202 | REG04 | TRN4 | J. Juarez | TBD | [5 empty] | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
N/A | PRD-slv8000 | REG01 | PRD1 | IBM-DBA | J. Brown | File System Bld | MfgPro Install | Add-On Mod | DS-Training | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS | DS
N/A | PRD-slv8000 | REG02 | PRD2 | IBM-DBA | TBD | File System Bld | MfgPro Install | Add-On Mod | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
N/A | PRD-slv8000 | REG03 | PRD3 | IBM-DBA | TBD |  |  |  | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
N/A | PRD-slv8000 | REG04 | PRD4 | IBM-DBA | TBD | File System Bld | MfgPro Install | Add-On Mod | Unavailable | Unavailable | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use | Not in Use
N/A | PRD-slv8000 | REG05 | PRD5 | IBM-DBA | V. Lu | File System Bld | MfgPro Install | Add-On Mod | TBD | TBD | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod | Korea-Prod
REG01 | Americas | US, Canada and Mexico | [12 empty] | GLD | Gold
REG02 | Europe | United Kingdom, Spain, Portugal and France | [12 empty] | DEV | Development
REG03 | Europe | Czech and Hungary | [12 empty] | CNV | Conversion
REG04 | Brazil | Brazil | [12 empty] | QA | CRP(Conf. Room Pilot)
REG05 | AP | Korea | [12 empty] | PRD | Production
http://cov7102.columbus.visteon.com:8080/databaseschedule.html
http://cov7102.columbus.visteon.com:8080/DatabaseStatus.html
Updated
10/05/2007